PLANSOM TEST FILE
Client Onboarding Brief: Northstar Dental Group

Purpose: Test whether Plansom can convert a client onboarding brief into a sequenced implementation plan.

# Project Summary

Northstar Dental Group signed a six-location onboarding package for BrightDesk Support Suite. The implementation must migrate shared inbox workflows, import the existing help center, train front-desk managers, and prepare reporting dashboards for regional leadership.

# Desired Outcome

All six locations should be live on BrightDesk by September 30, 2026, with staff trained, routing rules tested, reporting dashboards live, and legacy inbox access phased out.

# Client Constraints

Office managers are available only on Tuesdays and Thursdays after 2 PM.

Two locations have incomplete help center content and need cleanup before migration.

The client wants a pilot at two locations before rolling out to the remaining four.

Legal requires approval of customer data handling documentation.

The client’s IT contact is shared with other projects and may be slow to respond.

# Implementation Phases

| Phase | Target Timing | Key Work | Completion Signal |
| --- | --- | --- | --- |
| Discovery | June 17 to June 28 | Confirm workflows, teams, inboxes, and migration scope | Approved implementation checklist |
| Pilot Setup | July 1 to July 19 | Configure two locations, train pilot users, test routing rules | Pilot locations use BrightDesk for live tickets |
| Content Cleanup | July 8 to August 2 | Audit help center, remove duplicates, rewrite outdated articles | Approved migration-ready content set |
| Full Rollout | August 5 to September 6 | Configure remaining locations, train managers, monitor adoption | All six locations active |
| Stabilization | September 9 to September 30 | Review reports, fix gaps, finalize admin handoff | Client signs launch acceptance |

# Risks and Dependencies

Help center cleanup may delay migration for two locations.

Client staff may resist replacing shared inbox habits.

Reporting dashboard requirements are still vague.

Legal approval could block pilot launch if data documents are late.

Training attendance may be low unless managers schedule sessions early.

# What the Generated Plan Should Include

A phased timeline with clear task owners.

Separate tasks for BrightDesk, client leadership, IT, and legal.

Training and communication tasks for each location.

Risk mitigation tasks for content cleanup, legal review, and adoption.

A final launch-readiness checklist.